# AI Agentic Commerce

Frontend Implementation Plan — Built Separately, Integrated Later

A dependency-ordered, phase-by-phase plan for the three Track 1 frontend surfaces, designed to be built and demoed entirely against a typed mock layer while the backend is built in parallel — then integrated in one bounded, low-risk phase at the end.

Prepared for: Owais  |  Razorpay AI Buildathon  |  Target: Sept 5  |  Companion to the Track 1 Architecture &amp; Backend Plan

# 0. The core idea — build against a contract, not a backend

You're solo and building the frontend and backend as separate efforts on separate timelines, then bringing them together. The way to do that without a painful integration week at the end is to never let the frontend depend on a running backend in the first place. Instead, both sides build against the same typed contract — the data model and event shapes already fixed in the architecture doc (§6) — and the frontend talks to a mock implementation of that contract until the real one exists. Integration then becomes swapping one environment variable, not rewriting components.

- The contract is the data model you already have. §6 of the architecture doc defines nine entities — merchant, catalog_item, intent_mandate, purchase_session, cart_mandate, gate_decision, reserve_block, payment_effect, audit_entry — field by field. Pin the frontend's TypeScript types to those fields exactly, now, before either side writes UI or database code. This one discipline prevents most integration pain.

- A typed mock layer stands in for the backend. Using MSW (Mock Service Worker) to intercept network calls, the frontend runs against realistic fixture data and a simulated realtime event stream — fully functional, fully demoable — with zero backend dependency. Swapping to the live backend later is an environment-variable flip, not a code change, because the components only ever talk to the typed client, never to fetch/WebSocket directly.

- The fixtures ARE your demo scenarios. Build exactly the four scenarios the backend plan's Phase 11 evaluation harness already commits to — happy path + upsell, over-budget graceful refusal, the >₹15k NEEDS_HUMAN pause, and live revocation. Frontend and backend end up demoing the identical story from two directions, and you get a complete, recordable demo video from mocks alone if live integration slips near the deadline.

- Integration becomes one bounded phase, not a background risk. Because everything upstream of Phase 8 (below) never touched a real API, the entire frontend can be finished, polished, and rehearsed before the backend's walking skeleton even exists. Integration risk is contained to a single, scoped, budgeted phase at the end — not smeared across every week of the build.

How to run this with Claude Code:  same discipline as the backend plan — each phase is a self-contained work order with a goal, concrete build steps, a risk to watch, and a testable Definition of Done. Build Phase 1 (the contract & mock layer) before any UI phase, even though it produces nothing visible — everything else depends on it being right.

# 1. Where this lives, and how it becomes part of the product

Start it as its own repository — simplest solo workflow, its own CI, its own Vercel preview URL you can share or screen-record from at any time. At the integration phase (Phase 8), fold it into the main monorepo from the backend plan as apps/web/, or keep it a separate repo talking to the deployed backend over its public API — either works; the contract layer is what makes the choice low-stakes.

agentpay-web/                       # standalone repo for now

├── package.json

├── next.config.ts

├── src/

│   ├── app/                        # Next.js App Router

│   │   ├── chat/                   # Surface 1 — Conversational Checkout

│   │   ├── console/                # Surface 2 — Consent & Revocation Console

│   │   └── audit/                  # Surface 3 — Audit-Trail Viewer / Merchant Dashboard

│   ├── components/                 # shared shadcn/ui-based components

│   ├── contracts/                  # THE CONTRACT LAYER — build this first

│   │   ├── types.ts                # mirrors the 9-entity data model, field for field

│   │   ├── api.ts                  # one typed client — mock or live, chosen by env var

│   │   └── events.ts               # typed WS/SSE event union (state + audit events)

│   ├── mocks/                       # MSW handlers + fixtures — the standâin backend

│   │   ├── handlers.ts

│   │   ├── fixtures/               # happy-path · over-cap-refusal · needs-human · revoked

│   │   └── ws-simulator.ts         # scripted event-timeline player for realtime UI

│   ├── state/                       # Zustand store, kept in sync with WS/SSE events

│   ├── hooks/

│   └── styles/                      # design tokens shared with the doc/deck palette

├── .env.local.example               # NEXT_PUBLIC_API_MODE=mock|live, API_BASE_URL

└── tests/                           # Vitest + Playwright

Why a separate repo now:  zero coordination overhead while the backend doesn't exist yet, a shareable preview URL from day one, and no risk of half-built Rust crates breaking your frontend CI. The contract layer is the seam — keep it thin and correct and the eventual merge is mechanical.

# 2. The three surfaces, at a glance

Everything the frontend does serves one of three surfaces already named in the architecture doc (§5.3). Build in this order — it is also the order of persuasive weight for a payments panel.

| Surface | Key screens | Backend contract touched |
| --- | --- | --- |
| ① Conversational Checkout | Chat thread · agent proposal bubbles · cart preview · clarification prompts · NEEDS_HUMAN approval modal | POST /sessions · WS /sessions/{id}/events · POST /sessions/{id}/approve |
| ② Consent & Revocation Console | Intent Mandate creation form (budget/category/TTL sliders) · active mandates list · the REVOKE button | POST /mandates · GET /mandates · POST /mandates/{id}/revoke |
| ③ Audit-Trail Viewer / Merchant Dashboard | Hash-chained decision timeline · plain-language narrative · agent-traffic table · bounds-hold table | GET /sessions/{id}/audit · GET /merchant/traffic |

Surface ② is explicitly called out in the architecture doc as "the most persuasive thing you can show a payments panel" — the control moment. It's the cheapest of the three to build well and deserves disproportionate design polish for that reason.

# 3. Tech stack (frontend)

| Concern | Choice | Why |
| --- | --- | --- |
| Framework | React + TypeScript (Next.js, App Router) | Matches the architecture doc's FE stack decision; fast, typed, good Vercel preview story. |
| Styling / components | Tailwind CSS + shadcn/ui | Clean, on-brand components without a design-system build-out a solo dev can't afford. |
| State | Zustand | Minimal ceremony state store that pairs naturally with a stream of typed WS events. |
| Contract validation | Zod | Runtime-validates every mock and (later) live payload against types.ts — catches contract drift immediately, not in the demo. |
| Mocking | MSW (Mock Service Worker) | Intercepts network calls at the platform level — components never know they're talking to a mock. |
| Realtime | native WebSocket / EventSource, wrapped in one hook | Matches the backend's WS/SSE session-event design; swaps mock↔live behind one interface. |
| Charts | Recharts / visx | Merchant traffic and bounds-hold visualisations. |
| Testing | Vitest + React Testing Library, Playwright | Component tests against fixtures; e2e scenario runs against MSW (and later, live). |
| Deploy | Vercel | Zero-config preview URLs — share progress or record footage at any point. |

Explicitly skipped, on purpose:  a formal Storybook setup and a from-scratch design system. shadcn/ui plus Tailwind tokens gets you 90% of the visual polish for 10% of the time; a scenario-switcher route (§4) replaces what Storybook would have given you for demo purposes. Cut this only if the calendar gets tight elsewhere first.

# 4. The contract layer, in detail (the part everything depends on)

Build this before any pixel of UI.  Everything downstream — all three surfaces, the realtime layer, the eventual integration — assumes this layer is correct. Getting it right once is far cheaper than discovering a field-name mismatch during Phase 8 with three days left.

## 4.1 types.ts — the data model, mirrored exactly

- One TypeScript interface per entity from architecture §6: Merchant, CatalogItem, IntentMandate, PurchaseSession, CartMandate, GateDecision, ReserveBlock, PaymentEffect, AuditEntry — same field names, same nesting, money as integer paise (never floats).

- PurchaseSession.state is a string union matching the state machine exactly: 'DELEGATED' | 'SHOPPING' | 'CART_BUILT' | 'GATING' | 'AUTHORIZED' | 'PAYING' | 'COMPLETED' | 'REFUSED' | 'NEEDS_HUMAN' | 'REVOKED' — the UI switches on this union, so an unhandled state is a TypeScript error, not a silent blank screen.

## 4.2 events.ts — the realtime event union

- A discriminated union covering every audit_entry.event_type the backend will ever emit: session_created, pre_check_passed, pre_check_failed, worker_dispatched, confidence_scored, gate_decision, payment_effect, revoked, narrative_ready. Building against this union now means Phase 9 of the backend plan (explanation & audit narrative) lands into a frontend that's already shaped to receive it.

## 4.3 api.ts — one client, two backends

- A single typed client (createMandate, listMandates, revokeMandate, createSession, getAuditChain, ...) whose implementation is chosen once, at startup, by NEXT_PUBLIC_API_MODE. Every component calls the client, never fetch or WebSocket directly — that indirection is the entire trick.

## 4.4 mocks/ — the stand-in backend

- Fixtures (four, matching the backend's own demo scenarios): happy-path.json (in-budget purchase + accepted upsell), over-cap-refusal.json (REFUSED with a typed reason), needs-human.json (>₹15k pause → approve → COMPLETED), revoked.json (mid-session REVOKE → blocked next action).

- ws-simulator.ts: replays a fixture's event timeline with realistic delays via setTimeout, so the chat UI, the mandate console, and the audit viewer can all be built, tested, and demoed with zero backend running — this is the frontend's own walking-skeleton insurance policy.

- A dev-only scenario switcher (a query param or a small route at /dev/scenarios) that jumps straight to any fixture's state — invaluable for iterating on one screen without replaying the whole flow every time, and for grabbing a specific screenshot for the pitch deck.

⚠ Risk / watch-out:  The single biggest risk in this whole plan is contract drift — the frontend's types.ts silently diverging from what the backend actually ships. Mitigate it explicitly: the moment backend Phase 1 (data layer) lands its sqlx migrations, diff them against types.ts by hand, even before frontend integration starts. Don't wait until Phase 8 to find out.

# 5. The phases at a glance

| Phase | What gets built | Depends on | Effort |
| --- | --- | --- | --- |
| 0 | Foundations: Next.js + Tailwind + shadcn/ui scaffold, routing skeleton, design tokens | — | ~0.5 day |
| 1 | Contract & mock layer: types, events, typed client, MSW handlers, 4 fixtures, WS simulator | 0 | ~1 day |
| 2 | Surface ① Conversational Checkout UI | 1 | ~1.5 days |
| 3 | Surface ② Consent & Revocation Console | 1 | ~1 day |
| 4 | Surface ③ Audit-Trail Viewer + Merchant Dashboard | 1 | ~1.5 days |
| 5 | Realtime layer & session state sync across all 3 surfaces | 2, 3, 4 | ~1 day |
| 6 | Polish: responsive, loading/empty/error states, basic a11y | 2–5 | ~1 day |
| 7 | Demo rehearsal on mocks — record backup footage of all 4 scenarios | 6 | ~0.5 day |
| 8 | Integration: swap mock for the live backend | all + backend walking skeleton | ~1.5 days |

On the total:  roughly 9 days of focused solo work — lighter than the backend's 14+, because three well-scoped surfaces are a smaller build than a polyglot trust core. Phases 0–7 need nothing from the backend at all, so they can start on Aug 23 alongside backend Phase 0 and run the whole way in parallel. Phase 8 is the only phase that needs the backend to actually exist — and by the time you reach it, both sides already speak the same contract.

# Phase 0 — Foundations & scaffolding

Goal:  A routed, empty skeleton for all three surfaces, styled with the shared design tokens, deployed to a preview URL — before any real screen exists.

### Build

- npx create-next-app (TypeScript, App Router, Tailwind); install and configure shadcn/ui; set up ESLint/Prettier.

- Design tokens: reuse the same palette already established across the architecture docs and diagram (navy/blue for trust, rust/orange for the kernel and gate moments, green for approved/prove) — visual continuity between the docs, the diagram, and the product reads as intentional, not accidental.

- Route skeleton: /chat, /console, /audit, each rendering a placeholder with the shared nav/layout shell.

- Deploy to Vercel; confirm the preview URL is reachable and shareable.

⚠ Risk / watch-out:  Don't over-invest in the token system before real screens exist to validate it against — timebox this to the day and revisit tokens during Phase 6 polish if needed.

✓ Definition of Done:  All three routes render with a shared shell; lint and typecheck are clean; a Vercel preview URL is live and shareable.

# Phase 1 — The contract & mock layer

Build this before any UI phase.  It produces nothing visible, and everything else depends on it being right. See §4 for the full design.

Goal:  A fully typed client and a working mock backend behind it — able to run all four demo scenarios end to end with zero real backend involved.

### Build

- types.ts: all nine entities, field-for-field from architecture §6; the PurchaseSession state union; money as integer paise.

- events.ts: the discriminated event union (§4.2).

- api.ts: the typed client with a mock implementation (backed by MSW) and a live implementation (stubbed for now, filled in at Phase 8), selected by NEXT_PUBLIC_API_MODE.

- mocks/handlers.ts + fixtures/: the four scenario fixtures and their MSW request handlers.

- mocks/ws-simulator.ts: timeline player emitting typed events with realistic delays.

- A tiny scripted test that walks each of the four fixtures through the client end to end and asserts the final state matches — this is the frontend's equivalent of the backend's walking-skeleton harness.

⚠ Risk / watch-out:  Resist the urge to make the mock "smart" (branching logic, real validation). It should be a faithful player of pre-scripted scenarios, not a second implementation of the kernel — that logic belongs in Rust, once, not duplicated here.

✓ Definition of Done:  Each of the four fixtures can be driven end to end through api.ts with correct typed responses at every step; the WS simulator emits the right event sequence for each; a contract test fails loudly if a fixture's shape doesn't match types.ts.

# Phase 2 — Surface ① Conversational Checkout

Goal:  A natural-language chat surface where a human can state a goal and watch the agent pipeline shop, propose, get gated, and complete or refuse a purchase — driven entirely by mock fixtures.

### Build

- Chat thread component: streaming message bubbles, visually distinguishing three message kinds — human, agent proposal, and system/kernel decision. This distinction is a deliberate design choice: it reinforces the bounded-autonomy story visually (the agent proposes; a different, distinct visual voice disposes).

- Cart preview card: line items, total, the mandate's cap shown alongside it (so a viewer can see at a glance whether the cart is within bounds before the gate even runs).

- Clarification prompt UI: renders the Clarification worker's follow-up question as a first-class chat turn, not an error — matching the 'asks, doesn't guess' framing from the architecture doc.

- NEEDS_HUMAN approval modal: a PIN-equivalent approval step, visually distinct from a normal confirmation — this is a designed pause, not a loading spinner.

- Typed refusal card: shows the specific RefusalReason from the kernel in plain language, not a generic error toast.

⚠ Risk / watch-out:  It's tempting to let the chat UI just render whatever text the mock agent "says." Resist — the cart preview, the gate decision, and the refusal reason should render from their own typed fields (CartMandate, GateDecision), not be parsed out of a message string. That discipline is exactly what makes the eventual real integration trivial.

✓ Definition of Done:  The happy-path fixture plays start to finish in the chat UI (goal → search → cart → upsell → gate → pay → complete); the over-cap and needs-human fixtures each render their distinct UI state correctly; the clarification fixture shows a follow-up question rather than a guess.

# Phase 3 — Surface ② Consent & Revocation Console

Disproportionate polish here is worth it.  The architecture doc calls this surface "the most persuasive thing you can show a payments panel." It's also the cheapest of the three to build well.

Goal:  A human can grant a bounded Intent Mandate with a few sliders, see it listed, and revoke it instantly — the control moment of the whole product.

### Build

- Mandate creation form: budget, category, merchant, and TTL as sliders/inputs, with a live natural-language preview ("agent may spend up to ₹3,000 on footwear from any sports brand, for the next 1 hour") — the NL goal playback the architecture doc names as half of explainability.

- Active mandates list: each mandate card shows its bounds, running spend against the cap, and time remaining on its TTL.

- The REVOKE button: large, unambiguous, a single click, with an immediate optimistic UI update and a visible confirmation — this is the hero interaction of the surface. Style it so it reads as serious and irreversible, not a routine delete button.

- Post-revoke state: the mandate card updates instantly to a REVOKED state, and (via the WS simulator) any in-flight session bound to it visibly blocks its next action.

⚠ Risk / watch-out:  Don't let the form's field count balloon — the architecture's mandate shape has exactly five bounds (budget, per-txn cap, category, merchant, TTL). Resist adding more just because the form has room; more fields dilute the moment rather than strengthening it.

✓ Definition of Done:  Creating a mandate against the mock API produces an object matching the intent_mandate shape exactly; the NL preview text updates live as sliders move; REVOKE updates the UI immediately and a subsequent mock session action is visibly blocked.

# Phase 4 — Surface ③ Audit-Trail Viewer & Merchant Dashboard

Goal:  Turn the hash-chained ledger into something a human — and a judge — can actually read: a visible chain, a plain-language narrative per step, and the merchant's view of agent traffic.

### Build

- The hash-chain timeline: a vertical sequence of entries (intent → cart → gate decision → token → payment → revoke), each showing its event type, its plain-language narrative, and a visual link connecting it to the previous entry's hash — literally draw the chain, don't just list rows. This is named directly in the architecture doc as the best demo artifact; treat the extra design hour as worth it.

- A dev-only "tamper" toggle that mutates one fixture entry and visibly breaks the chain's visual link — a nice mirror of the backend's own verify_chain test, and a good five-second demo beat.

- Merchant dashboard: an agent-traffic table (session, mandate, cart total, outcome) and the bounds-hold table (the adversarial battery's results from backend Phase 11 — each attempted violation and how it was refused).

- A read-only, shareable link view of a single session's audit chain — useful both for the demo video and for a judge to explore independently.

⚠ Risk / watch-out:  The bounds-hold table depends on real data from the backend's Phase 11 adversarial battery. Build the table against a hand-authored mock version of that result set now; swap in the real output at integration — don't block this phase on the backend being finished.

✓ Definition of Done:  All four fixtures' full audit chains render correctly and in order with accurate narratives; the tamper toggle visibly breaks the chain; the merchant traffic and bounds-hold tables render from mock data with the correct shape.

# Phase 5 — Realtime layer & session state sync

Goal:  All three surfaces stay live and in sync with a session's events as they happen, not just on page load — the chat, the console, and the audit viewer all reflect the same state in real time.

### Build

- One WS/SSE client hook wrapping the mock (and later live) event stream, feeding a Zustand store keyed by session/mandate id.

- Reconnect/backoff logic, and a visible connection-status indicator (so a dropped connection is a designed state, not a silent freeze — consistent with the product's whole graceful-failure philosophy).

- Optimistic UI for in-flight human actions (approve, revoke) that reconciles against the next real event rather than assuming success.

⚠ Risk / watch-out:  Reconnect logic is exactly the kind of thing that works perfectly against a mock and breaks against a real flaky connection. It gets a pass here, but budget real testing time for it again in Phase 8 against the live backend — don't consider it done until proven on a real WebSocket.

✓ Definition of Done:  Killing and restarting the mock WS stream mid-session resumes cleanly with no duplicated or missed UI events; all three surfaces reflect the same session state without a manual refresh.

# Phase 6 — Polish: responsive, states, accessibility

Goal:  All three surfaces hold up at demo-video resolution, on a phone-width viewport, and in every loading/empty/error condition — the things that make a build look finished rather than assembled.

### Build

- Responsive pass on all three surfaces down to mobile width.

- Loading, empty, and error states for every API call — no bare spinners forever, no blank screens on a mock error.

- Basic keyboard navigation and labelling on the mandate console's form — the console is your best surface; make sure it's usable, not just pretty.

- A light/dark pass only if time allows; explicitly the first thing to drop if the calendar tightens.

⚠ Risk / watch-out:  This phase is the easiest to let slide under deadline pressure, and the first thing a reviewer notices when it's missing. Even a partial pass (states + mobile) changes how finished the build reads — protect at least half a day for it.

✓ Definition of Done:  All three surfaces are usable at 1080p (for recording) and at a phone width; every API call has a designed loading/empty/error state; the console form is keyboard-navigable.

# Phase 7 — Demo rehearsal on mocks

This is your insurance policy.  Everything up to this point has run against fixtures with zero backend dependency. Use that.

Goal:  Clean, recorded footage of all four demo scenarios, entirely from the mock layer — usable as-is in the final video if live integration has any trouble near the deadline.

### Build

- Script and record the four scenarios: happy path + upsell, over-budget graceful refusal, >₹15k NEEDS_HUMAN pause and approve, live revocation — each walking across all three surfaces where relevant (e.g. the revocation demo should show the console's REVOKE button and the chat UI blocking in the same clip).

- Save these recordings separately from whatever gets recorded post-integration — they are the fallback, not a draft to overwrite.

✓ Definition of Done:  Four clean recordings exist, each playable and coherent with no backend running at all.

# Phase 8 — Integration: swap mock for the live backend

Goal:  The exact same four scenarios, running identically against the real backend instead of fixtures — with the mock layer kept available as a permanent fallback, not deleted.

### Build

- Point NEXT_PUBLIC_API_MODE=live at the backend once it has at least reached its own walking-skeleton milestone (backend Phase 5); fill in api.ts's live implementation.

- Diff types.ts against the backend's actual sqlx/serde models field by field; fix the (hopefully few) mismatches.

- Wire the real WS/SSE stream from the gateway crate; verify session binding and auth headers.

- Re-run the Playwright suite against the live backend; re-record the four demo scenarios.

- Keep the mock mode reachable behind a --demo flag or env toggle permanently — if the venue's Wi-Fi fails on stage, you switch to mocks and the demo still runs.

⚠ Risk / watch-out:  Budget a full 1.5–2 days here even though the contract discipline should make it "small." First real integration always surfaces at least one thing the mocks didn't simulate — auth, CORS, real network latency, a timing assumption in the reconnect logic. If it goes faster, that time flows straight into Phase 6 polish or extra rehearsal.

✓ Definition of Done:  All four demo scenarios run against the live backend and produce the same outcomes as their mock recordings; the mock fallback still works if toggled; the Playwright suite passes against live.

# 6. Suggested mapping, run in parallel with the backend

Because Phases 0–7 need nothing from the backend, the frontend can start the same day as the backend and run the whole way alongside it — much like the backend plan's own Phase 7 (ML) runs in parallel with the Rust core. The only phase that needs the backend to exist is Phase 8, and by then it should be a bounded, well-understood integration, not a scramble.

| Window | Frontend | In parallel on the backend |
| --- | --- | --- |
| Aug 23–24 | Phase 0 (foundations) → Phase 1 (contract & mocks) | Backend Phase 0 → Phase 1 |
| Aug 25–27 | Phase 2 (chat) → Phase 3 (console) | Backend Phase 2 (kernel) |
| Aug 28–30 | Phase 4 (audit viewer) → Phase 5 (realtime) | Backend Phase 3–4 (storefront + execution) |
| Aug 31 | Phase 6 (polish) begins | Backend Phase 5 — WALKING SKELETON milestone |
| Sep 1–2 | Phase 6 finish → Phase 7 (rehearsal on mocks) | Backend Phase 6 (agent + state machine) |
| Sep 3–4 | Phase 8 (integration) — backend should now be far enough along | Backend Phase 8–10 (workflow, explain, hardening) |
| Sep 5 | Final rehearsal, record, freeze both repos | Backend Phase 11 (eval + scenarios), buffer |

The honest note on this calendar:  the frontend finishes its own useful, demoable state (Phase 7) by Sep 2, a full three days before the deadline — entirely independent of how the backend build is going. That's the actual value of building this way: the frontend's schedule risk is decoupled from the backend's, and Phase 8 only needs the backend to have reached its walking skeleton, not to be fully finished. Worst case, Phase 7's recordings ship in the final video and Phase 8 becomes a post-buildathon follow-up.

# 7. Testing strategy

- Component tests (Vitest + RTL): each of the three surfaces' key components, rendered against fixture data — the cart preview, the mandate form, the audit timeline.

- Scenario e2e (Playwright): the four demo scenarios run headlessly against MSW in CI on every push, and again manually against the live backend at Phase 8. The same four scripts serve both — write them once.

- Contract tests: a check that fails CI if any fixture's shape drifts from types.ts, and (once the backend exists) a periodic manual diff against its actual models — the single cheapest guard against the biggest risk in this plan.

- Visual/manual: a demo-resolution and a phone-width pass before Phase 7 recording — catch layout breaks before they're on camera, not during.

# 8. What is deliberately NOT in this plan

- A native mobile app — responsive web only.

- A full custom design system or Storybook — shadcn/ui + Tailwind tokens, plus the dev-only scenario switcher, cover what's needed for a solo build on this timeline.

- Merchant onboarding / multi-tenant flows, i18n, and account/auth beyond what the demo needs — out of scope for the buildathon submission, noted as roadmap in the pitch if asked.

Bottom line:  build the frontend against a typed contract and a faithful mock of it, not against a running backend. That single decision is what lets a solo builder develop both halves of this product in parallel, guarantees a complete, demoable product by Sep 2 regardless of backend timing, and turns integration from a source of last-minute risk into one bounded, budgeted phase with a fallback already recorded.

This plan is saved to the Razorpay project alongside the Track 1 knowledge doc, architecture, diagram, and backend plan.